## Implementation timeline
Implementation Timetable
Project | Building a healthy and resilient Cook Islands community - one block at a time
Version
COMPONENTS/OUTPUTS | Project Year 1 |  |  |  | Project Year 2 |  |  |  | Project Year 3 |  |  |  | Project Year 4 |  |  |  | Project Year 5 |  |  |  | Post-Project
| Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2
Component 1: Strengthening the capacity and capabilities of the Ministry of Health, partners and stakeholders to integrate climate change considerations in their health operations
Output 1.1: Existing health policies, plans and programmes include strategies that are informed by current and projected climate change
1.1.1: Conduct a baseline assessment regarding existing legislation, policies and plans of Te Marae Ora to identify and evaluate strategies and indicators to address climate sensitive health outcomes | Project Year 1 Q1: Baseline assessment conducted
1.1.2: Draft update to Climate Change and Health Adaptation Plan 2012 | Project Year 1 Q2: Update to Govt
1.1.3: Update TMO policies, plans and procedures to include climate-sensitive health risks | Project Year 2 Q2: Updated policies
1.1.4: Development of TMO communications strategy and implementation plan | Project Year 2 Q3: Comms strategy; Project Year 3 Q2: Materials developed in field
Output 1.2: TMO health intelligence integrates HIS with meteorological and climate information for health early warnings and CSHR forecasting
1.2.1: Assess health intelligence needs to integrate CSHRs | Project Year 1 Q4: Draft specification; Project Year 2 Q1: Full specification for augmented HIS
1.2.2: Develop a data management and dissemination system for augmented health intelligence incorporating CSHRs | Project Year 1 Q4: Systems design complete; Project Year 2 Q2: System implemented
1.2.3: Conduct TMO analyst training and train staff in hospitals and clinics in augmented health intelligence | Project Year 2 Q4: Staff trained in HIS
Output 1.3: Staff in TMO and partner organizations apply climate change information
1.3.1: Develop targeted CC&H educational programme to increase capacity of health sector workforce and partners | Project Year 2 Q1: Materials developed; Project Year 2 Q3: Update materials; Project Year 3 Q3: Update materials; Project Year 4 Q3: Update materials; Project Year 5 Q3: Update materials
1.3.2: Deliver CC&H educational programming, environmental health training, and other professional development at TMO | Project Year 2 Q1: Training; Project Year 2 Q4: Training; Project Year 3 Q3: Training; Project Year 4 Q3: Training; Project Year 5 Q3: Training
Component 2: Building institutional capabilities to respond to climate change & health issues and effectively deliver health services to the population of the Cook islands
Output 2.1: Health Centres in the Pa Enua are resilient to CC impacts
2.1.1: Complete detailed technical design for improvements to health facilities to achieve CC resilience | Project Year 1 Q2: Design completed inclusive of ESAP screening process; Project Year 2 Q2: Design completed inclusive of ESAP screening process; Project Year 3 Q2: Design completed inclusive of ESAP screening process; Project Year 4 Q2: Design completed inclusive of ESAP screening process; Project Year 5 Q2: Design completed inclusive of ESAP screening process
2.1.2: Upgrade and provision health facilities to achieve CC resilience | Project Year 2 Q1: Health Centres upgraded - Mauke, Rakahanga, Rarotonga; Project Year 3 Q1: Health Centres upgraded -Atiu, Manihiki (2x); Project Year 4 Q1: Health Centres upgraded -Mitiaro, Rarotonga; Project Year 5 Q1: Health Centres upgraded -Aitutaki, Palmerston, Penrhyn, Rarotonga; Project Year 5 Q4: Health Centres upgraded -Mangaia, Pukapuka, Penrhyn, Nassau
Output 2.2: TMO information systems have high availability
2.2.1: Provide TMO headquarters with high availability IT infrastructure for HIS and health intelligence | Project Year 2 Q2: Design finalized
2.2.2: Supply health facilities with resilient information systems to ensure uninterrupted health services before, during and after extreme weather events | Project Year 2 Q4: Local facilities installed
Output 2.3: TMO capacity built via environment laboratory and mobile testing
2.3.1: Assess mobile laboratory testing equipment needs | Project Year 2 Q2: Specification complete
2.3.2: Provide mobile environmental testing kits to assess water quality | Project Year 2 Q4: Testing kist distributed
Component 3: Resilience building measures to reduce health impacts from climate change in communities
Output 3.1: Existing TMO health outreach and community care strengthened to cover CSHRs
3.1.1: Augment existing HPO/EHO manuals and tools to integrate indicators on CSHRs | Project Year 2 Q4: Manuals and tools updated
3.1.2: Train HPOs/EHOs in the use of augmented tools | Project Year 3 Q1: Training of HPOs/EHOs in the use of augmented tools
Output 3.2: Communities and people throughout the Cook Islands are aware of climate change impacts on health and of ways to reduce the impact
3.2.1: Communicate risk reduction options relevant to CSHRs and disseminate/share evidence-based practices | Project Year 2 Q2: Develop communication risk reduction programme; Project Year 2 Q3: Vaka Voyaging; Project Year 2 Q4: Communication risk reduction sessions; Project Year 3 Q2: Vaka Voyaging; Project Year 3 Q4: Communication risk reduction sessions; Project Year 4 Q2: Vaka Voyaging; Project Year 4 Q4: Communication risk reduction sessions; Project Year 5 Q2: Vaka Voyaging
3.2.2: Design and implement non-clinical health and wellbeing activities to address CSHRs | Project Year 2 Q1: Training workshop Raro home gardens; Project Year 2 Q2: Training workshop Pa Enua home gardens; Project Year 2 Q4: Hydroponics kit for Northern Group; Project Year 3 Q1: Training workshop Raro home gardens; Project Year 3 Q2: Training workshop Pa Enua home gardens; Project Year 4 Q1: Training workshop Raro home gardens; Project Year 4 Q2: Training workshop Pa Enua home gardens; Project Year 5 Q1: Training workshop Raro home gardens; Project Year 5 Q2: Training workshop Pa Enua home gardens
3.2.3: Promote healthy diets in the Cook Islands | Project Year 2 Q3: Community outreach for non-clinical health and wellbeing activities to address CSHRs; Project Year 3 Q3: Community outreach for non-clinical health and wellbeing activities to address CSHRs; Project Year 4 Q3: Community outreach for non-clinical health and wellbeing activities to address CSHRs; Project Year 5 Q3: Community outreach for non-clinical health and wellbeing activities to address CSHRs
Output 3.3: Sharing lessons learned with other sectors in Cook Islands and the Pacific Community
3.3.1: Sharing CC&H resilience knowledge products and experiences from this programme | Project Year 2 Q1: Activities to be undertaken in the context of other meetings and opportunities
3.3.2: Participate in regional events to share lessons learned | Project Year 2 Q1: Activities to be undertaken in the context of other meetings and opportunities
Project Monitoring* | Project Year 1 Q2: Inception Report; Project Year 2 Q1: APR; Project Year 3 Q1: APR; Project Year 3 Q3: Interim Evaluation; Project Year 4 Q1: APR; Project Year 5 Q1: APR; Post-Project Q1: Completion Report; Post-Project Q2: Final Evaluation
APR = Annual Performance Report
*In addition to this monitoring requirements, the Funded Activity is also subject to financial reporting per the AMA/FAA, such as Unaudited/Audited Financial Statements, Financial information reports, and other reports as defined in the FAA.
Note on C22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Design of Health Centres should note that they must also follow the 5. Screening Methodology and Integration of Environmental Social Safeguards this means that prior to design completed it has screened all the activities. Just include the words during design phase.